## Sheet1
Jaimy T | Testing Results: | Russel (16-5-2022) | Sanjiv (19-5-2022)
Pass | - DAO account registration : OK | Pass
Pass | - Minting and transfer :
Pass | - Token Minting : OK | Pass
Pass | - Recipient Contract deployment : OK | Pass
Pass | - Says Badge Tranferred, but I cant see the Badges in the Assets in the Recipient wallet | Not Passed
Pass | - The mint file not immediately visible in the ONE Rep Files Menu (see video) | Not Passed
Pass | - Re minting (Using the same file with changed token numbers)
Pass | - Recipient Contract Deployment done again, as we discussed, this is supposed to be a one time activity for one recipient, We should save the contract address on the first mint and check when file is uploaded and attach if available. | Not Passed
(see video)
Pass | - DAO Cordinator : It works, but the ONERep board is not visible to the contributors | Partial , need fix
| - Super Admin access : Waiting for your response on adding the wallet I gave as super admin coordinator - NOT TESTED | NOT TESTED
Cosmetic changes :
Pass | Dapp Contract Name : ONERep
Account Registration
Pass | - Make the wallet address non editable once captured. This is to prevent the user changing it.
Pass | - We need a popup message after "Deploy Token" with message "DAO Token deployed, please proceed to launch ONERep Account"
Pass | - Keep the "Launch ONERep Account" button disabled till the Badge Address is displayed and above popup displayed
Pass | - Keep Badge Address field non editable.
Pass | - Rename the name of the Dapp as "OneRep" (favicon and Menu)
Pass | - OneRep Files : Display full URI of the IPFS file, clickable to open IPFS location
Pass | - OneRep Files : Correct the spelling to "ONERep Files (Cordinape), Remove the lorem ipsum text as well
Pass | - OneRep Board : Remove the lorem ipsum text
Pass | - OneRep Board : Display the DAO Name by default on the dropdown as there is only one DAO
Pass | - OneRep Board : Token Name displayed is not same as the Badge Name entered during registration. What is DAOCoin ?
During Minting and Transfer
Pass | - At Step 3 we should wait for the whole minting process to be over to display the message "Minting Done" and should showing the wait widget while the process is happening.
Pass | - Update the status of the file only once the whole process is successful
Pass | - Update the records in ONERep board only when the whole process is successful